## Read me
Part 10 of 10 — Consolidated RACI
What this is | Every RACI assignment from Parts 2 to 9 in one matrix: 172 steps against 30 roles.
Reading it | R does the work. A is accountable, and where a gate exists this is the gate's primary approver. C is consulted before. I is informed after. Blank means not involved.
R today | In the Part 9 rows, 'R today' means the live build lets anyone signed in do it, where the specification names a specific officer.
Companions | Part 10 — Registers holds the gate register, the hard blocks and the live roles and people. Part 10 — Process register holds the steps, the deviations and the hand-offs.
Date | 8 September 2026.

## Consolidated RACI
Part | Step | Chief Executive Officer | Chief Operating Officer | Director | Vice President for Sales | Sales | Project Manager | Person In Charge | Design Manager | Design Engineer | Permit Liaison | Document Controller | Procurement Head | Procurement Officer | Warehouse Custodian | Safety Officer | Service Technician | Operations and Maintenance Lead | Human Resource Head | Line Manager | Payroll Officer | Head of Finance | Finance Officer | Console Holder | Employee | Anyone signed in (live build) | Client | Candidate | Supplier | Authority | Department of Labor and Employment
2 | 2.1 Account, contact, site |  |  |  | I | R / A
2 | 2.2 Opportunity |  |  |  | I | R / A
2 | 2.3 Start assessment |  |  |  | A | R | [20 empty] | I
2 | 2.4 Site access | [25 empty] | R
2 | 2.5 Site assessment |  |  |  | A | R | C
2 | 2.6 Proceed? |  |  |  | A | R
2 | 2.7 Lost / on hold |  |  | I | A | R
2 | 2.8 Create proposal |  |  |  | A | R | C | [14 empty] | C
2 | 2.9 Submit for review |  |  | I | I | R
2 | 2.10 Review proposal (G6) |  | C | A | I | I
2 | 2.11 Send to client |  |  | I | A | R | [20 empty] | I
2 | 2.12 Client decision |  |  |  | I | I | [20 empty] | R
2 | 2.13 Submit for won |  |  | I | I | R
2 | 2.14 Decide won (G7) |  |  | A | I | I | I | [14 empty] | I
2 | 2.15 Project created |  |  |  |  | I | I | [14 empty] | I
2 | 2.16 Create contract | [5 empty] | R / A | [14 empty] | C
2 | 2.17 Client signs | [5 empty] | I | [19 empty] | R
2 | 2.18 Attach signed contract (G9) | A |  |  |  |  | R | [14 empty] | I
2 | 2.19 Risk terms and review (G10) |  | C | A |  |  | R
2 | 2.20 Project parties |  |  | I |  |  | R / A
2 | 2.21 Advance from setup | [5 empty] | I | [14 empty] | I
3 | 3.1 Create package | [5 empty] | I |  | A | R
3 | 3.2 Work the package | [7 empty] | A | R
3 | 3.3 Add deliverables | [7 empty] | A | R
3 | 3.4 Professional seal | [5 empty] | I |  | C | R / A |  | I
3 | 3.5 Issue for review | [7 empty] | A | R
3 | 3.6 Deliverable review | [7 empty] | R / A | C
3 | 3.7 Issue for approval | [5 empty] | I |  | A | R
3 | 3.8 Submit design freeze | [5 empty] | I |  | I | R
3 | 3.9 Approve freeze (G18) | [5 empty] | I |  | C | A
3 | 3.10 Package released | [5 empty] | I |  | I | I |  | I
3 | 3.11 Bill of materials | [5 empty] | C |  | A | R
3 | 3.12 Permit type library | [9 empty] | R / A | C
3 | 3.13 Raise project permit | [5 empty] | I |  |  |  | R / A
3 | 3.14 Set requirements | [9 empty] | R / A | C
3 | 3.15 Library accumulates | [9 empty] | I | I
3 | 3.16 Requirements ready | [5 empty] | I |  |  |  | R / A
3 | 3.17 Engage consultant (G20) |  | A | C |  |  | I |  |  |  | R
3 | 3.18 Submit permit | [5 empty] | I |  |  |  | R / A | [18 empty] | I
3 | 3.19 Authority decides | [5 empty] | I |  |  |  | I | [18 empty] | R
3 | 3.20 Record decision | [5 empty] | I |  |  |  | R / A | I
3 | 3.21 Close permit | [5 empty] | I |  |  |  | R / A
3 | 3.22 Permit available to mobilisation | [5 empty] | R / A |  |  |  | I
4 | 4.1 Create purchase order | [5 empty] | C | [5 empty] | A | R | [14 empty] | I
4 | 4.2 Add order lines | [5 empty] | C | [5 empty] | A | R | C
4 | 4.3 Submit for approval | [5 empty] | I | [5 empty] | A | R
4 | 4.4 Approve — G4 ≤ ₱100,000 |  |  | C |  |  | I | [5 empty] | A | I
4 | 4.4 Approve — G5 > ₱100,000 |  | C | A |  |  | I | [5 empty] | C | I
4 | 4.5 Issue to supplier | [5 empty] | I | [5 empty] | A | R | I | [13 empty] | I
4 | 4.6 Supplier delivers | [11 empty] | I | I | I | [13 empty] | R
4 | 4.7 Record goods receipt | [5 empty] | I | C |  |  |  |  | I | C | R / A
4 | 4.8 Delivery status recomputed | [5 empty] | I | [5 empty] | I | I | I
4 | 4.9 Material readiness | [5 empty] | I | [5 empty] | C | I | I
4 | 4.10 Amend an issued order |  |  | C |  |  | C | [5 empty] | A | R | [14 empty] | I
4 | 4.11 Add bank account | [11 empty] | A | R
4 | 4.12 Confirm bank account |  |  | C | [8 empty] | R / A
4 | 4.13 Locations and catalogue | [11 empty] | C |  | R / A
4 | 4.14 Create stock transfer | [5 empty] | C | [7 empty] | R / A
4 | 4.15 Dispatch — G25a inter-island |  | C | A |  |  | C | [7 empty] | R
4 | 4.15 Dispatch — G25b within-island |  |  | C |  |  | A | [7 empty] | R
4 | 4.16 Receive at destination | [5 empty] | A | R | [6 empty] | I
4 | 4.17 Discrepancy flagged | [5 empty] | I | [5 empty] | I |  | I
4 | 4.18 Raise stock adjustment | [5 empty] | I | [7 empty] | R
4 | 4.19 Approve adjustment — G26 | [5 empty] | C | [7 empty] | A
4 | 4.20 Open physical count — G27 | [5 empty] | I | [7 empty] | R / A
4 | 4.21 Submit counted quantities | [6 empty] | C | [6 empty] | R
4 | 4.22 Close the count | [5 empty] | I | [7 empty] | R / A
4 | 4.23 Issue material to site | [5 empty] | A | C | [6 empty] | R
5 | 5.1 Raise resource request | [5 empty] | R | C | [10 empty] | A
5 | 5.2 Create deployment | [5 empty] | C | I | [10 empty] | R / A
5 | 5.3 Mobilise (HB1, HB4) |  |  | I |  |  | A | I | [7 empty] | C |  |  | R
5 | 5.4 Assign equipment | [5 empty] | A | R | [6 empty] | C
5 | 5.5 Stage becomes construction |  |  | I |  |  | A | I | [7 empty] | I |  |  | I
5 | 5.6 Open the site report | [5 empty] | I | R / A
5 | 5.7 Toolbox meeting | [5 empty] | I | R / A | [7 empty] | C |  |  | I
5 | 5.8 Day's activities | [5 empty] | C | R / A
5 | 5.9 Submit the report | [5 empty] | I | R / A | [7 empty] | I
5 | 5.10 Approve the report | [5 empty] | R / A | I
5 | 5.11 Block completion |  |  | I |  |  | I | I | [7 empty] | I
5 | 5.12 Days worked | [5 empty] | C | I | [10 empty] | I
5 | 5.13 Safety and Health Program (HB2) |  |  | C |  |  | A | I | [7 empty] | R |  |  | I | [11 empty] | R
5 | 5.14 Create permit to work | [5 empty] | I | C | [7 empty] | R / A
5 | 5.15 Issue the permit (G28) | [5 empty] | I | I | [7 empty] | A
5 | 5.16 Raise a safety stop | [5 empty] | I | R | [7 empty] | I
5 | 5.17 Lift the safety stop (G29) |  |  | I |  |  | I | I | [7 empty] | A
5 | 5.18 Record an incident |  |  | I |  |  | I | C | [7 empty] | R / A |  |  | I | [11 empty] | I
5 | 5.19 Report a near miss | [5 empty] | I | R | [7 empty] | A
5 | 5.20 Safety inspection | [5 empty] | I | C | [7 empty] | R / A
5 | 5.21 Corrective action | [5 empty] | C | R | [7 empty] | A
5 | 5.22 Raise non-conformance | [5 empty] | A | R | [7 empty] | C
5 | 5.23 Review the report |  |  | I |  |  | R / A | I | [7 empty] | C
5 | 5.24 Close the report (G19) |  |  | C |  |  | A | I | [7 empty] | C
5 | 5.25 No commissioning with an open report |  |  | I |  |  | A | I | [7 empty] | I
6 | 6.1 Billing milestone |  |  | I |  |  | C | [14 empty] | A | R |  |  |  | I
6 | 6.2 Raise progress claim |  |  | I |  |  | C | [14 empty] | A | R
6 | 6.3 Submit the claim (G11) |  |  | C |  |  | I | [14 empty] | A | R |  |  |  | I
6 | 6.4 Client certifies |  |  | I |  |  | I | [14 empty] | I | I |  |  |  | R / A
6 | 6.5 Record certification (G11) |  |  | C |  |  | I | [14 empty] | A | R |  |  |  | I
6 | 6.6 Mark paid |  |  | I |  |  | I | [14 empty] | A | R |  |  |  | I
6 | 6.7 Retention invoice (G12) |  | I | C |  |  | I | [14 empty] | A | R |  |  |  | I
6 | 6.8 Raise fund request |  |  | I |  |  | R | [14 empty] | R / A | C
6 | 6.9 Approve the request (G23) |  | I | C |  |  | I | [14 empty] | A | I
6 | 6.10 Release the funds |  |  | I |  |  | I | [14 empty] | A | R
6 | 6.11 Liquidate the advance |  |  | I |  |  | C | [14 empty] | A | R
6 | 6.12 Raise a write-off |  |  | I |  |  | C | [14 empty] | A | R
6 | 6.13 Approve — G1 ≤ ₱50,000 |  |  | C |  |  | I | [14 empty] | A | I
6 | 6.13 Approve — G2 ₱50,000–₱100,000 |  | C | A |  |  | I | [14 empty] | C | I
6 | 6.13 Approve — G3 > ₱100,000 |  | A | C |  |  | I | [14 empty] | C | I
6 | 6.14 Raise a variation order |  |  | I |  |  | R / A | [14 empty] | C | C |  |  |  | I
6 | 6.15 Approve the variation order (G8) |  | C | A |  |  | R | [14 empty] | C | I |  |  |  | I
6 | 6.16 Cash forecast |  | I | I |  |  | C | [14 empty] | A | R
6 | 6.17 Three-month gap |  | I | I |  |  | I | [14 empty] | I | I
6 | 6.18 Pay a supplier |  |  | I |  |  | I | [14 empty] | A | R
7 | 7.1 Requisition |  | I | [15 empty] | R / A | C |  | I
7 | 7.2 Add candidates | [17 empty] | R / A | C | [7 empty] | I
7 | 7.3 Interviews | [17 empty] | A | R | [7 empty] | C
7 | 7.4 Create the offer |  | I | [15 empty] | R / A | C |  | C | [5 empty] | I
7 | 7.5 Issue the offer (G24) |  | C | [15 empty] | A | I |  | C | [5 empty] | I
7 | 7.6 Candidate responds | [17 empty] | I | I | [7 empty] | R / A
7 | 7.7 Employee record | [17 empty] | R / A | I | I |  |  |  | I
7 | 7.8 Regularisation diarised |  | I | [15 empty] | A | R |  |  |  |  | I
7 | 7.9 Request leave | [17 empty] | I | A |  |  |  |  | R
7 | 7.10 Review the leave | [17 empty] | C | R / A |  |  |  |  | I
7 | 7.11 Write objectives | [17 empty] | I | A |  |  |  |  | R
7 | 7.12 Acknowledge objectives | [17 empty] | I | R / A |  |  |  |  | I
7 | 7.13 Quarterly review |  | I | [15 empty] | A | R |  |  |  |  | R
7 | 7.14 Engagement response |  | I | [15 empty] | I | [5 empty] | R / A
7 | 7.15 Enter the rate tables | [17 empty] | R / A |  | C | C
7 | 7.16 Approve the tables |  | I | [15 empty] | C |  | R | A
7 | 7.17 Open the period | [17 empty] | I | C | R / A | C |  |  | I
7 | 7.18 Add workers | [17 empty] | C | C | R / A |  |  |  | I
7 | 7.19 Run payroll ×3 | [17 empty] | I | I | R / A | I
7 | 7.20 Approve the period (G30) |  | A | [15 empty] | C | I | I | C |  |  | I
7 | 7.21 Acknowledge the payslip | [17 empty] | I | C | I |  |  |  | R / A
7 | 7.22 Disburse (G31) |  | C | [15 empty] | I |  | R | A |  |  | I
7 | 7.23 Protocol status change |  | I | [15 empty] | I |  | A | I
8 | 8.1 Commissioning complete |  | I | I |  |  | R / A | [9 empty] | I | I |  |  |  |  | I |  |  |  | I
8 | 8.2 Client accepts |  | C | A |  |  | R | [9 empty] | I | I |  |  |  |  | I |  |  |  | R
8 | 8.3 Turnover date (G21) |  | C | A |  |  | R | [9 empty] | I | I |  |  |  |  | I |  |  |  | I
8 | 8.4 Dates derived |  | I | I |  |  | I | [9 empty] | I | I |  |  |  |  | I |  |  |  | I
8 | 8.5 Retention invoice (G12) |  | I | C |  |  | C | [10 empty] | I |  |  |  |  | R / A |  |  |  | I
8 | 8.6 Maintenance schedule |  |  | I |  |  | I | [9 empty] | C | R / A | [8 empty] | I
8 | 8.7 Create a visit | [5 empty] | I | [9 empty] | R | A | [8 empty] | I
8 | 8.8 Work the visit | [5 empty] | I | [9 empty] | R | A | [8 empty] | C
8 | 8.9 Record readings | [5 empty] | I | [9 empty] | R | A | [8 empty] | I
8 | 8.10 Raise a defect |  | I | I |  |  | C | [9 empty] | R | A | [8 empty] | I
8 | 8.11 Submit for sign-off | [5 empty] | I | [9 empty] | R | I
8 | 8.12 Approve the sign-off (G34) |  |  | I |  |  | I | [9 empty] | I | A | [8 empty] | I
8 | 8.13 Next visit date | [15 empty] | I | I
8 | 8.14 Warranty claim (G34) |  | C | A |  |  | C | [9 empty] | C | R |  |  |  |  | I |  |  |  | I
8 | 8.15 The gate engine
9 | 9.1 First console holder | I | I | [20 empty] | R / A
9 | 9.2 Second console holder | C | C | I | [19 empty] | A |  | R today
9 | 9.3 Gate rows seeded | I | I | [20 empty] | I
9 | 9.4 Configure a gate (G31) | C | R / A | I | [7 empty] | I | [11 empty] | C |  | R today
9 | 9.5 Gates unconfigured | I | I | I | [7 empty] | I | [11 empty] | I
9 | 9.6 Change a constant (G22) | I | R / A | C | [19 empty] | I |  | R today
9 | 9.7 Constant by tool call | I | I | [20 empty] | I |  | R
9 | 9.8 The timeline |  | I
9 | 9.9 Assign a role (G24) | I | A | R | [19 empty] | C |  | R today
9 | 9.10 Screen path refuses | I | I | I | [19 empty] | I
9 | 9.11 Role by tool call | I | I | I | [19 empty] | I |  | R
9 | 9.12 Direct assignment | I | I | I | [19 empty] | R / A
9 | 9.13 Change permissions (G32) | R / A | C | I | [19 empty] | C |  | R today
9 | 9.14 Sidebar painted |  | I | [22 empty] | I
9 | 9.15 Classify a document (G33) |  | I | C | [7 empty] | R / A | [13 empty] | R today
9 | 9.16 Publish a revision |  | I | C | [7 empty] | A | [13 empty] | R today
9 | 9.17 Revision by tool call |  | I | [8 empty] | I | [13 empty] | R
9 | 9.18 Legal hold | C | C | I | [7 empty] | A | [13 empty] | R today
9 | 9.19 Audit chain | I | I | I | [7 empty] | I | [11 empty] | I
9 | 9.20 Cryptographic erasure | A | C | I | [19 empty] | C |  | R today
9 | 9.21 Export and attest | A | C | I | [7 empty] | I | [11 empty] | R |  | R today